## QC Summary _Formate
QC Daily Summary - 16 May 2026 (Yesterday's Reports)
Total: 32 ¦ PASS: 15 ¦ HOLD: 17 ¦ REJECT: 0
SL | Date | Vendor | Style | Job Order | Qty | Activity | Defects | Status | Inspector | Email | File
1 | 14-May-2026 | DesignTex | 1EOFDV02L | N/A | 1 (PP Sample, Size S) | PP Sample | Hairiness on cuff/bottom/neck edges; tighter knitting tension; wrong care label position; wavy/loose inside shoulder stitch; improper neck joint allowance; tight cuff starting; wavy side seam; iron pressing mark on sleeve | HOLD | Ripon Ghosh | Dear DesignTex Team, During the PP Sample evaluation conducted on 14 May 2026 for Style No. 1EOFDV02L (Sample Size: S), our QC team has identified the following issues that must be addressed before bulk production proceeds: Workmanship / Construction Issues: Hairiness on cuff, bottom, and neck edges Knitting tension too tight — needs to be corrected to spec Wavy / loose stitching on inside shoulder Improper neck joint allowance Tight cuff starting Wavy side seam Iron pressing mark visible on sleeve Trim / Label Issue: 8. Care label position is incorrect — does not match approved placement Please respond to the following by 19 May 2026: For each issue listed above, what is the root cause? What specific corrections will be made before the revised PP sample is submitted? When can we expect the corrected PP sample for re-evaluation? Will the care label placement be corrected per our approved tech pack — please confirm exact position? No bulk production should commence until a corrected PP sample is approved by our QC team. Please refer to the attached PP Sample evaluation report for full findings. Best regards, [Your Name] Quality Assurance Team Action Required: DesignTex to provide root cause + correction plan for all 8 issues, and submit revised PP sample for re-evaluation. Reply deadline: 19 May 2026. | 1EOFDV02L- PP Sample Approved comments-14- May- 2026 (Designtex).pdf
2 | 14-May-2026 | DELTA GALIL USA INC. / EVERFASHION | 3G680H00R, 3G681R02F, 3G681S03B, 3G681Z00E, 3G682H003, 3G682M002, 3G682S00N | Multiple (0626A01894, 0626A01886, 0626A01885, 0626A01884, 0626A01939, 0626A01938, 0626A01941, 0626A01952, 0626A01951, etc.) |  | Final Inspection | Two job orders failed inspection (JO 0626A01885 - 2514 pcs and JO 0626A01951 - 2597 pcs) | HOLD | BENETTON QC |  | Benetton Final Inspection Offering (05-17-2026).xls
3 | 14-May-2026 | TARASIMA | 4VGRUF06G |  | 21,800 | PP MEETING | GSM lower than required (379 vs 390); Shrinkage variance on Color-902 (L up to -2.86%); GPT test report pending; Test report balance for 902 color missing; Potential issues with uneven wash, puckering at side pocket, slanted waist loops, uneven bottom hem allowance | HOLD | AL AMIN |  | FW26 _4VGRUF06G_PP MEETING REPORT _TARASIMA.pdf
4 | 14-May-2026 | TALISMAN | 4L4H557R4 | 4L4H557R4 | 125 | Finishing inline | Uneven width waist band edge (2), uneven gap at zipper tape (2), looseness at side seam (1), pulled yarn at pocket bag | HOLD | NAZMUL HAQ RABIN | Dear TALISMAN Team, During the Finishing Inline Inspection conducted on 14 May 2026 for Style No. 4L4H557R4 / PO 4L4H557R4 (Qty inspected: 125 pcs), our QC team identified the following workmanship defects: Defects Found: #DefectPieces Affected1Uneven width at waistband edge22Uneven gap at zipper tape23Looseness at side seam14Pulled yarn at pocket bagNot quantified Please respond to the following by 19 May 2026: What is the root cause of each defect listed above — particularly the waistband unevenness and zipper tape gap? How many pieces in the current production lot are affected by the pulled yarn at pocket bag? What immediate corrective action has been taken on the already-finished stock? What process controls are being implemented to prevent recurrence in remaining production? From which lot/batch can consistent improvement be confirmed? Please refer to the attached inline inspection report for full findings. | FW26-4L4H557R4- Finishing inline report -Talisman.pdf
5 | 13-May-26 | CONCEPT KNITTING LTD. | 3KHYC205W | 26S_1648 | 125 | Final Inspection | Faded print at front, puckering at sleeve hem, badly done seam, badly ironing, uneven stripe at side seam, uneven sleeve length, pleat at bottom, untrimmed thread at pocket, looseness at sleeve cuff | HOLD | MD. RAIHAN KHAN |  | FW26_ 3KHYC205W_ Commessa_ 26A_1648_ Final Random Inspection Report_ CONCEPT KNITTING LTD..pdf
6 | 13-May-26 | CONCEPT KNITTING LTD. | 3TNHL108D | 26S_1095 | 80 | Final Inspection | Asymmetric neck shape (1), Asymmetric shoulder forward (1), Unpaired (1), Wrong packing (1) - Total 4 defects | HOLD | Md. Raihan Khan |  | FW26_ 3TNHL108D_ Commessa_ 26A_1095_ Final Random Inspection Report_ CONCEPT KNITTING LTD..pdf
7 | 16-May-2026 | Laila style ltd | 49F9GF03A | 26-A-2452 | 125 | Finishing inline | Washing mark at bottom hem; Skip stitch at bottom hem; Pull yarn at waistband; Rawedge out at waistband inside; Unclean at back pocket inside; Uncut thread | HOLD | Jakir |  | FW26_ 49F9GF03A_Finishing Inline Report_Laila style ltd.pdf
8 | 16-May-2026 | OCEAN SWEATER IND. LTD. | 1LU4C501D | 26_A_1700 | 125 | Final Inspection | Contermation yarn at sleeve; hairiness at bottom edge; dirty stain at back; poor trim at neck & ragline joint; poor trim at placket edge; flat needle at ragline seam; single fly at neck; needle drop at neck; inner placket visible; asymmetries neck shape | HOLD | Sadeour Rahman |  | FW26_1LU4C501D Commessa_ 26A_1700_Final Random Inspection Report_OCEAN SWEATER IND. LTD..pdf
9 | 16-May-2026 | Designtex Knitwear Ltd. | 1S9ZD204W | 26_A_2004 | 125 | Final Inspection | Badly done seam (wavy armhole, wrong linking at neck, open side seam), dropped stitches at neck (7), badly ironing, puckering at sleeve top, unstitching at size label, pulled threads | HOLD | ANICHUL HAQ FEROZ |  | FW26_1S9ZD204W_ Commessa_ 26-A_2004_ Final Random Inspection Report_Result_Designtex.pdf
10 | 14-May-2026 | EVER FASHION LTD (DELTA) | 3G681S03B | 26_A_1938 | 125 | Final Inspection | Puckering at waist band and leg opening elastic application; dropping at leg opening elastic; unclean raw edge at inside waist seam; uncut thread at waist band | HOLD | N/A |  | FW26_3G681S03B_Commessa_26A_1938_Final Random Inspection Report_EVER FASHION (DELTA).pdf
11 | 16-May-2026 | EVER FASHION LTD (DELTA) | 3G682S00N | 26_A_1958 | 398 | Final Inspection | Badly done seam (puckering at waist seam), badly ironing at back panel, pulled threads minor (uncut thread at leg opening) | HOLD | N/A |  | FW26_3G682S00N_Commessa_26A_1958_Final Random Inspection Report_EVER FASHION (DELTA).pdf
12 | 14-May-26 | Concept Knitting Ltd. | 3KHYC205W | 26_A_1649 | 125 | Final Inspection | Asymmetrical shoulder shape; Wavy at over bottom; Poor attachment at front pocket; Front stripe round shape; Uncut thread; Pulled threads minor | HOLD | Sadeour Rahman |  | FW26_3KHYC205W Commessa_ 26A_1649_ Final Random Inspection Report_CONCEPT KNITTING LTD..pdf
13 | 14-May-26 | Concept Knitting Ltd. | JUNIOR BOY FELPA CHIUSA (3KHYC205W) | 26_A_1650 | 125 | Final Inspection | Wavy at shoulder seam, wavy at over bottom, back part visible at front, front stripe up-down, badly ironing | HOLD | Sadeour Rahman |  | FW26_3KHYC205W Commessa_ 26A_1650_ Final Random Inspection Report_CONCEPT KNITTING LTD..pdf
14 | 14-May-26 | Concept Knitting Ltd. | 3KHYC205W | 26_A_1651 | 125 | Final Inspection | Uneven topstitch at neck, miss print, asymmetric position at front pocket, cutting sticker found inside pocket, badly done seam | HOLD | Aminul Islam Topu |  | FW26_3KHYC205W_ Commessa_ 26A_1651_Final Random Inspection Report_CONCEPT.pdf
15 | 16-May-2026 | TALISMAN | 4L4HDF07F |  | 80 | Sewing Inline | Looseness at waistband; V-shape at waistband mouth; Up-down at waist mouth; Skip stitch at side seam O/L; Inseam crotch point up-down; Slanted brand label attach; Slanted bk pkt bone; Seam point up-down at waist/side seam/bottom hem; Uneven gap at inside waistband; Visible bottom hem blind stitch; Visible waistband hidden stitch | HOLD | MD. Selim Reza |  | FW26_4L4HDF07F_Sewing Inline Report_ TALISMAN.pdf
16 | 11-May-2026 | Ocean Sweater (Pvt.) Ltd. | 1UWVQ10AF |  | 14085 | PP MEETING | Measurement found some points out of tolerance; side seam wavy not acceptable; seam allowance must not exceed 0.5 cm; linking tension must be normal (10cm pulled to 13cm) | HOLD | Ripon Ghosh |  | FW_1UWVQ10AF.B.B PP_Meeting Report_ Ocean sweater_Ltd..pdf
17 | 12-May-2026 | Valmont Sweater Ltd. | 12D5U202D |  | 2000 |  | Looseness at front & back raglan seams; side seam wavy not accepted; GPT reports (color fastness, pilling, twisting/tearing/seam slippage) pending | HOLD | Sadeour Rahman |  | SS26_12D5U202D. Meeting Report_ Valmont sweater_Ltd..pdf
18 | 15-Apr-2026 | DESIGNTEX KNITWEAR LTD | 1EOFDV02L |  | N/A | Technical sheet | None | PASS | Sambin Sabina |  | 1EOFDV02L TS.pdf
19 | 06-May-2026 | OCEAN SWEATER IND. (PVT.) LTD. | 1UWVQ10AF |  | N/A | Technical sheet | None | PASS | Gosh Ripon |  | 1UWVQ10AF TS.pdf
20 | 16-May-2026 | DELTA TEXTILE BULGARIA LTD | 3G682M002 | 3G682M002.B.B | N/A |  | None | PASS | Howlader Mohammed Tanvir |  | 3G682M002_Delta.pdf
21 | 17-May-26 | Designtex Knitwear Ltd. | 1S9ZD204W, 1S9ZD301W, 1S9ZD502Z, 1S9ZE204X | 0626A02001, 0626A02005 | 42998 |  | None | PASS | N/A |  | Final Inspection and PP Meeting Plan_Vendor Name.xlsx
22 | 14-May-2026 | Sterling | 4HEMDF0CP | 26/A/2087 | 3235 |  | Unclean at side seam (1 min); Looseness at front facing, Roping at side seam, Hiking at bottom hem (Badly done seam); Shiny mark at garments (Badly ironing) | PASS | N/A |  | FW26( Base )_4HEMDF0CP_Commessa_26A_2087_Finaln Random Inspection Report_Sterling..pdf
23 | 14-May-2026 | Sterling |  | 26/A/2088 | 125 |  | Joint stitch at bottom hem; Hiking at bottom hem; Uncut thread at side seam | PASS | JAKIR |  | FW26( Base )_4HEMDF0CP_Commessa_26A_2088_Finaln Random Inspection Report_Sterling..pdf
24 | 13-May-2026 | Sterling |  | 26/A/2089 | 715 |  | Roping at side seam; H. Drop stitches | PASS | JAKIR |  | FW26( Base )_4HEMDF0CP_Commessa_26A_2089_Finaln Random Inspection Report_Sterling..pdf
25 | 11-May-2026 | Ocean sweater |  | 26_A_1704 | 125 |  | Badly done seam, Yarn contamination, Pulled yarn, Hi-low at bottom hem joint | PASS | Ripon Ghosh |  | FW26_1LU4C10AB_ Commessa_ 26-A_1704_ Final Random Inspection Report_Ocean sweater.pdf
26 | 14-May-2026 | EVER FASHION LTD (DELTA) |  | 26_A_1894 | 47 |  | None | PASS | FOKRUL |  | FW26_3G680H00R_Commessa_26A_1894_Final Random Inspection Report_EVER FASHION (DELTA).pdf
27 | 14-May-2025 | TALISMAN |  | 26 A 1844 | 125 |  | 1 Badly done seam (Major) - raw edge out at side seam; 1 Pulled threads minor - uncut thread | PASS | SELIM REZA |  | FW26_58YAUQ07E_Commessa_26A_1844_Final Random Inspection Report_TALISMAN..pdf
28 | 14-May-2025 | TALISMAN |  | 26 A 1847 | 489 |  | 11 minor defects total | PASS | SELIM REZA |  | FW26_58YAUQ07E_Commessa_26A_1847_Final Random Inspection Report_TALISMAN..pdf
29 | 16-May-2026 | Valmont Sweaters Ltd. |  | 4218938684 | 1 |  | None | PASS | N/A |  | ITALY WAYBILL 42 1893 8684.pdf
30 | 16-May-2026 | BANDEJJIA TRADERS |  | 102693973 | 2502 |  | Major (4): peel off/wrinkle inside, pasting open at front, bubbling loose at outside quarter, wrinkle at inside lining. Minor (5): back strap center out, glue marks, bubbling, color spell at pictogram | PASS | N/A |  | MOVIMODA_TRACKER_RE-INSPECTION_BANDEJJIA TRADERS _102693973_16-05-2026.xlsx
31 | 16-May-2026 | Ocean Sweater Ind. (Pvt.) Ltd. | 1PQ1B101N, 1UWVQ10AF (2598), 1PEUC10AG (2599) | DHL: 26 2366 4691 | 12 |  | None | PASS | Abed |  | Ocean Sweater sample - Invoice (16 May 26).xlsx
32 | 07-Apr-2026 | VALMONTFE |  | Multiple JOs | 34499 |  | None | PASS | N/A |  | PPM & Final Inspection Offering Sheet (07.04.26).xlsx
Legend: | GREEN = PASS |  | YELLOW = HOLD |  | RED = REJECT

## QC Summary
QC Daily Summary - 16 May 2026 (Yesterday's Reports)
Total: 32 ¦ PASS: 15 ¦ HOLD: 17 ¦ REJECT: 0
SL | Date | Vendor | Style | Job Order | Qty | Defects | Status | Inspector | Remarks | File
1 | 14-May-2026 | DesignTex | 1EOFDV02L - Benetton Women Donna D067 | N/A | 1 (PP Sample, Size S) | Hairiness on cuff/bottom/neck edges; tighter knitting tension; wrong care label position; wavy/loose inside shoulder stitch; improper neck joint allowance; tight cuff starting; wavy side seam; iron pressing mark on sleeve | HOLD | Ripon Ghosh | PP Sample Approved with comments for bulk production subject to improvements. Approved Tag No: 014103. Archive sample required from bulk with best workmanship, to be checked and signed by Benetton QC. | 1EOFDV02L- PP Sample Approved comments-14- May- 2026 (Designtex).pdf
2 | 14-May-2026 | DELTA GALIL USA INC. / EVERFASHION | 3G680H00R, 3G681R02F, 3G681S03B, 3G681Z00E, 3G682H003, 3G682M002, 3G682S00N | Multiple (0626A01894, 0626A01886, 0626A01885, 0626A01884, 0626A01939, 0626A01938, 0626A01941, 0626A01952, 0626A01951, etc.) | 34474 | Two job orders failed inspection (JO 0626A01885 - 2514 pcs and JO 0626A01951 - 2597 pcs) | HOLD | BENETTON QC | Mixed results: most lots PASS, 2 lots FAILED on 14-May; 5.16.2025 sheet lots pending status | Benetton Final Inspection Offering (05-17-2026).xls
3 | 14-May-2026 | TARASIMA | MAN PANTALONE LUNGO (4VGRUF06G) | 4VGRUF06G | 21,800 | GSM lower than required (379 vs 390); Shrinkage variance on Color-902 (L up to -2.86%); GPT test report pending; Test report balance for 902 color missing; Potential issues with uneven wash, puckering at side pocket, slanted waist loops, uneven bottom hem allowance | HOLD | AL AMIN | PP Meeting for FW26 Benetton style. Pending: GPT test report, color fastness/pilling reports, and test report balance for color 902. Bulk fabric must be relaxed 24 hours before cutting. 100% finished garments to pass metal detection. Pay attention during bulk production for SPI, waist loops, bottom hem, and wash consistency. | FW26 _4VGRUF06G_PP MEETING REPORT _TARASIMA.pdf
4 | 14-May-2026 | TALISMAN | Woman Pantalone lungo | 4L4H557R4 | 125 | Uneven width waist band edge (2), uneven gap at zipper tape (2), looseness at side seam (1), pulled yarn at pocket bag | HOLD | NAZMUL HAQ RABIN | Finishing inline inspection; defects must be corrected otherwise goods will be failed in final stage | FW26-4L4H557R4- Finishing inline report -Talisman.pdf
5 | 13-May-26 | CONCEPT KNITTING LTD. | 3KHYC205W - Boy Felpa Chiusa | 26S_1648 | 125 | Faded print at front, puckering at sleeve hem, badly done seam, badly ironing, uneven stripe at side seam, uneven sleeve length, pleat at bottom, untrimmed thread at pocket, looseness at sleeve cuff | HOLD | MD. RAIHAN KHAN | 24 cartons inspected; multiple minor and major defects found across manufacture and appearance categories | FW26_ 3KHYC205W_ Commessa_ 26A_1648_ Final Random Inspection Report_ CONCEPT KNITTING LTD..pdf
6 | 13-May-26 | CONCEPT KNITTING LTD. | 3TNHL108D - WOMAN T-SHIRT | 26S_1095 | 80 | Asymmetric neck shape (1), Asymmetric shoulder forward (1), Unpaired (1), Wrong packing (1) - Total 4 defects | HOLD | Md. Raihan Khan | AQL Acceptable; QC pass qty 73 pcs; 1 QC carton sealed with Movimoda gum tape; Goods HOLD due to individual size short maximum 65.3% | FW26_ 3TNHL108D_ Commessa_ 26A_1095_ Final Random Inspection Report_ CONCEPT KNITTING LTD..pdf
7 | 16-May-2026 | Laila style ltd | Boy Pantalone lungo (49F9GF03A) | 26-A-2452 | 125 | Washing mark at bottom hem; Skip stitch at bottom hem; Pull yarn at waistband; Rawedge out at waistband inside; Unclean at back pocket inside; Uncut thread | HOLD | Jakir | Finishing inline inspection; multiple minor defects found across cleanliness, seams, and manufacture categories | FW26_ 49F9GF03A_Finishing Inline Report_Laila style ltd.pdf
8 | 16-May-2026 | OCEAN SWEATER IND. LTD. | JUNIOR GIRL MAGLIA APERTA | 1LU4C501D / 26_A_1700 | 125 | Contermation yarn at sleeve; hairiness at bottom edge; dirty stain at back; poor trim at neck & ragline joint; poor trim at placket edge; flat needle at ragline seam; single fly at neck; needle drop at neck; inner placket visible; asymmetries neck shape | HOLD | Sadeour Rahman | Final Random Inspection, Level II (P5); 15 cartons inspected; multiple major and minor defects found across material, seams, and appearance | FW26_1LU4C501D Commessa_ 26A_1700_Final Random Inspection Report_OCEAN SWEATER IND. LTD..pdf
9 | 16-May-2026 | Designtex Knitwear Ltd. | 1S9ZD204W - Maglia polo | 26_A_2004 | 125 | Badly done seam (wavy armhole, wrong linking at neck, open side seam), dropped stitches at neck (7), badly ironing, puckering at sleeve top, unstitching at size label, pulled threads | HOLD | ANICHUL HAQ FEROZ | Inspected 13 cartons (06,10,16,21,31,37,42,48,54,57,60,63,65); Level II (P5) AQL; multiple major and minor defects found | FW26_1S9ZD204W_ Commessa_ 26-A_2004_ Final Random Inspection Report_Result_Designtex.pdf
10 | 14-May-2026 | EVER FASHION LTD (DELTA) | 3G681S03B - WOMAN SLIP | 26_A_1938 | 125 | Puckering at waist band and leg opening elastic application; dropping at leg opening elastic; unclean raw edge at inside waist seam; uncut thread at waist band | HOLD | N/A | Level II (P5) inspection, 9 cartons inspected; multiple minor/major defects found in seams and appearance | FW26_3G681S03B_Commessa_26A_1938_Final Random Inspection Report_EVER FASHION (DELTA).pdf
11 | 16-May-2026 | EVER FASHION LTD (DELTA) | 3G682S00N - MAN SLIP | 26_A_1958 | 398 | Badly done seam (puckering at waist seam), badly ironing at back panel, pulled threads minor (uncut thread at leg opening) | HOLD | N/A | Inspected boxes: 2, 7, 12, 16 = 04 CTN; Level II (P5), Final Random Inspection | FW26_3G682S00N_Commessa_26A_1958_Final Random Inspection Report_EVER FASHION (DELTA).pdf
12 | 14-May-26 | Concept Knitting Ltd. | JUNIOR BOY FELPA CHIUSA (3KHYC205W) | 26_A_1649 | 125 | Asymmetrical shoulder shape; Wavy at over bottom; Poor attachment at front pocket; Front stripe round shape; Uncut thread; Pulled threads minor | HOLD | Sadeour Rahman | QC carton qty-05, closed by Movimoda gum tape. 18 cartons inspected. Contact: Mr. Monir | FW26_3KHYC205W Commessa_ 26A_1649_ Final Random Inspection Report_CONCEPT KNITTING LTD..pdf
13 | 14-May-26 | Concept Knitting Ltd. | JUNIOR BOY FELPA CHIUSA (3KHYC205W) | 26_A_1650 | 125 | Wavy at shoulder seam, wavy at over bottom, back part visible at front, front stripe up-down, badly ironing | HOLD | Sadeour Rahman | QC carton qty-05, closed by Movimoda gum tape. 18 cartons inspected. Contact: Mr. Monir | FW26_3KHYC205W Commessa_ 26A_1650_ Final Random Inspection Report_CONCEPT KNITTING LTD..pdf
14 | 14-May-26 | Concept Knitting Ltd. | 3KHYC205W - Boy Felpa | 26_A_1651 | 125 | Uneven topstitch at neck, miss print, asymmetric position at front pocket, cutting sticker found inside pocket, badly done seam | HOLD | Aminul Islam Topu | As per AQL this commessa is Passed. Total 05 cartons sealed with Movimoda tape as QC carton with 120 pcs garments. Goods are held due to GPT pending. | FW26_3KHYC205W_ Commessa_ 26A_1651_Final Random Inspection Report_CONCEPT.pdf
15 | 16-May-2026 | TALISMAN | 4L4HDF07F - WOMAN PANTALONE | 700 | 80 | Looseness at waistband; V-shape at waistband mouth; Up-down at waist mouth; Skip stitch at side seam O/L; Inseam crotch point up-down; Slanted brand label attach; Slanted bk pkt bone; Seam point up-down at waist/side seam/bottom hem; Uneven gap at inside waistband; Visible bottom hem blind stitch; Visible waistband hidden stitch | HOLD | MD. Selim Reza | Inline inspection - fix process immediately and alert line QC to check defects carefully at process and end table | FW26_4L4HDF07F_Sewing Inline Report_ TALISMAN.pdf
16 | 11-May-2026 | Ocean Sweater (Pvt.) Ltd. | Girl Maglia - Ocean sweater | 1UWVQ10AF | 14085 | Measurement found some points out of tolerance; side seam wavy not acceptable; seam allowance must not exceed 0.5 cm; linking tension must be normal (10cm pulled to 13cm) | HOLD | Ripon Ghosh | PP Meeting for FW 2026 UCB Bambino, 7GG 3PLY 2/32 100% Acrylic, colors 901-904. Garments must pass 100% metal detection. Follow PK31, MP1 & MP2 packing instructions. Respect measurement spec. | FW_1UWVQ10AF.B.B PP_Meeting Report_ Ocean sweater_Ltd..pdf
17 | 12-May-2026 | Valmont Sweater Ltd. | Uomo Man Maglia (12D5U202D) | 01 COMESSA | 2000 | Looseness at front & back raglan seams; side seam wavy not accepted; GPT reports (color fastness, pilling, twisting/tearing/seam slippage) pending | HOLD | Sadeour Rahman | PPS approved; yarn 80% Cotton 20% Wool 2/30, 7GG 3ply; GPT test reports must be submitted before bulk production; linking tension 10cm after pulling 13cm | SS26_12D5U202D. Meeting Report_ Valmont sweater_Ltd..pdf
18 | 15-Apr-2026 | DESIGNTEX KNITWEAR LTD | 1EOFDV02L.B.B - Abito (1 pezzo) - Woman Dress | D067 | N/A | None | PASS | Sambin Sabina | Technical Specification Sheet approved on 15/04/2026. Half cardigan stitch, 80% Wool 20% Polyamide, RWS Certified, Made in Bangladesh. Production approved by Zanchetta Lorena. | 1EOFDV02L TS.pdf
19 | 06-May-2026 | OCEAN SWEATER IND. (PVT.) LTD. | 1UWVQ10AF - Striped Sweater Junior Girl | 1UWVQ10AF.B.B | N/A | None | PASS | Gosh Ripon | Technical Specification Sheet - Production status. Approved on 03/02/2026 by Ceccon Raffaella. Production released on 14/04/2026 by Quaglio Fabio. 100% Acrylic, Made in Bangladesh, Season 2026 AI. | 1UWVQ10AF TS.pdf
20 | 16-May-2026 | DELTA TEXTILE BULGARIA LTD | INTIMO UOMO DELTA - BI PACK T-SHIRT | 3G682M002.B.B | N/A | None | PASS | Howlader Mohammed Tanvir | Technical specification sheet for Undercolors Man Maglia m/corta, 95% Cotton 5% Elastane, Made in Bangladesh, Season 2026 AI | 3G682M002_Delta.pdf
21 | 17-May-26 | Designtex Knitwear Ltd. | 1S9ZD204W, 1S9ZD301W, 1S9ZD502Z, 1S9ZE204X | 0626A02001, 0626A02005 | 42998 | None | PASS | N/A | Final Inspection, Finishing Inline, and Showroom sample review scheduled at 10:00 AM | Final Inspection and PP Meeting Plan_Vendor Name.xlsx
22 | 14-May-2026 | Sterling | 4HEMDF0CP - Woman pantalone navetta | 26/A/2087 | 3235 | Unclean at side seam (1 min); Looseness at front facing, Roping at side seam, Hiking at bottom hem (Badly done seam); Shiny mark at garments (Badly ironing) | PASS | N/A | Random inspection Level II (P5); 32 cartons inspected | FW26( Base )_4HEMDF0CP_Commessa_26A_2087_Finaln Random Inspection Report_Sterling..pdf
23 | 14-May-2026 | Sterling | Woman pantalone navetta | 26/A/2088 | 125 | Joint stitch at bottom hem; Hiking at bottom hem; Uncut thread at side seam | PASS | JAKIR | Goods passed as per AQL. 08 cartons (182-189) sealed with Movimoda QC tape containing 123 pcs garments. | FW26( Base )_4HEMDF0CP_Commessa_26A_2088_Finaln Random Inspection Report_Sterling..pdf
24 | 13-May-2026 | Sterling | Woman pantalone navetta | 26/A/2089 | 715 | Roping at side seam; H. Drop stitches | PASS | JAKIR | Goods passed as per AQL. 05 cartons (44-48) sealed with Movimoda tape as QC carton with 79 pcs garments. | FW26( Base )_4HEMDF0CP_Commessa_26A_2089_Finaln Random Inspection Report_Sterling..pdf
25 | 11-May-2026 | Movimoda | Ocean sweater | 26_A_1704 | 125 | Badly done seam, Yarn contamination, Pulled yarn, Hi-low at bottom hem joint | PASS | Ripon Ghosh | As per AQL goods are passed. QC check qty: 119 pcs. QC CTN: 04 CTN closed by MOVIMODA gum tape. | FW26_1LU4C10AB_ Commessa_ 26-A_1704_ Final Random Inspection Report_Ocean sweater.pdf
26 | 14-May-2026 | EVER FASHION LTD (DELTA) | BOY CANOTTA | 26_A_1894 | 47 | None | PASS | FOKRUL | As per AQL goods are acceptable; QC carton qty-01, closed by Movimoda gum tape | FW26_3G680H00R_Commessa_26A_1894_Final Random Inspection Report_EVER FASHION (DELTA).pdf
27 | 14-May-2025 | TALISMAN | MAN CAMICIA | 26 A 1844 | 125 | 1 Badly done seam (Major) - raw edge out at side seam; 1 Pulled threads minor - uncut thread | PASS | SELIM REZA | Final Random Inspection, Level II (P5), AQL 1.5/2.5; 25 cartons inspected; Destination: Italy | FW26_58YAUQ07E_Commessa_26A_1844_Final Random Inspection Report_TALISMAN..pdf
28 | 14-May-2025 | TALISMAN | MAN CAMICIA | 26 A 1847 | 489 | 11 minor defects total | PASS | SELIM REZA | As per AQL goods are accepted. 5 cartons sealed with Movimoda tape as QC carton with 48 pcs garments. | FW26_58YAUQ07E_Commessa_26A_1847_Final Random Inspection Report_TALISMAN..pdf
29 | 16-May-2026 | Valmont Sweaters Ltd. | Sample of Sweater | 4218938684 | 1 | None | PASS | N/A | DHL Express Worldwide shipment from Valmont Sweaters Ltd. (Bangladesh) to Benetton Group SRL (Italy); 0.5 kg sample sweater, declared value 1.00 USD, DAP terms | ITALY WAYBILL 42 1893 8684.pdf
30 | 16-May-2026 | BANDEJJIA TRADERS | ERSILA WOMEN ANKLE BOOT - YELLOW | 102693973 | 2502 | Major (4): peel off/wrinkle inside, pasting open at front, bubbling loose at outside quarter, wrinkle at inside lining. Minor (5): back strap center out, glue marks, bubbling, color spell at pictogram | PASS | N/A | Final re-inspection passed with 4 major and 5 minor defects within acceptable limits | MOVIMODA_TRACKER_RE-INSPECTION_BANDEJJIA TRADERS _102693973_16-05-2026.xlsx
31 | 16-May-2026 | Ocean Sweater Ind. (Pvt.) Ltd. | 1PQ1B101N, 1UWVQ10AF (2598), 1PEUC10AG (2599) | DHL: 26 2366 4691 | 12 | None | PASS | Abed | Sample invoice to Benetton Operations SRL; Total value $74.70; Samples without commercial value | Ocean Sweater sample - Invoice (16 May 26).xlsx
32 | 07-Apr-2026 | VALMONTFE | Multiple styles (Sisley & Benetton) | Multiple JOs | 34499 | None | PASS | N/A | Multi-sheet offering schedule covering PPM, PPS Check, Finishing Inline and Final Inspection across several dates | PPM & Final Inspection Offering Sheet (07.04.26).xlsx
Legend: | GREEN = PASS |  | YELLOW = HOLD |  | RED = REJECT